## Sheet1
Days | Dates of Execution | Alternative Dates of Execution | Phase Distribution | Mode Of Delivery | Topics To Be Covered | Self Paced Content Mapped / Topics that a mentor would cover | Duration (Incl. Assignment & MCQ Assessment in self paced) | Time to be devoted
Monday | 2020-07-13 | 2020-07-20 | Phase 1 | Self Paced | Introductory Foundation Program : Java | Java for beginners: Step–by–step hands–on guide to Java | 8:00 | 2:00
Tuesday | 2020-07-14 | 2020-07-21 | [5 empty] | 3:00
Wednesday | 2020-07-15 | 2020-07-22 | [5 empty] | 3:00
Thursday | 2020-07-16 | 2020-07-23 |  |  | IO, Collections, Java 5 features | Ultimate Java Master Class | 5:00 | 2:00
Friday | 2020-07-17 | 2020-07-24 |  |  | Exceptions, Serialization |  |  | 3:00
Monday | 2020-07-20 | 2020-07-27 |  | Doubt clearing session VILT for those who couldn’t clear MCQ assessment - 2 Hours
Tuesday | 2020-07-21 | 2020-07-28 |  | VILT | JAVA 8 Multithreading & Concurrency JDBC Servlet, JSP Junit Design Patterns | Lambda Expression Functional Interface Method Reference Streams Optional Class Default Methods Static Methods (Interface) Date Time API Base64 Multiprocessing vs Multitasking vs Multithreading What is Java Thread Creating and Starting Java Threads Thread life cycle Race Conditions Synchronized Blocks Producer Consumer problem Introduction to SQL Creating Database and Tables CRUD operations on database Alter table schema Joins Validate and test database schema Test an RDBMS Dataconstraints with Database Testing SQL Injection - Database Security Testing What is Http, Web, Server, Web Server, Application Server What is Servlet Installation of tomcat First Servlet Handle parameters Life cycle Login page Validation Session Management RequestDispatcher and sendRedirect() What is Jsp Advantages & disadvantages of JSP over Servlet Life cycle Directives Actions Implicit Objects CRUD application The purpose of software tests What is Junit Test Cases Ignore Test Assert statements Test suites Parameterized test Creational design patterns - Builder - Factory Method - Singleton Structural design patterns - Adapter - Bridge - Composite - Decorator Behavioral design patterns - Chain of responsibility - State - Visitor | 2:00 | 2:00
Wednesday | 2020-07-22 | 2020-07-29 |  |  |  |  | 2:00 | 2:00
Thursday | 2020-07-23 | 2020-07-30 |  |  |  |  | 2:00 | 2:00
Friday | 2020-07-24 | 2020-08-04 |  |  |  |  | 2:00 | 2:00
Monday | 2020-07-27 | 2020-08-05 |  |  |  |  | 2:00 | 2:00
Tuesday | 2020-07-28 | 2020-08-06 |  |  |  |  | 2:00 | 2:00
Wednesday | 2020-07-29 | 2020-08-07 |  |  |  |  | 2:00 | 2:00
Thursday | 2020-07-30 | 2020-08-10 |  |  |  |  | 2:00 | 2:00
Tuesday | 2020-08-04 | 2020-08-12 |  |  |  |  | 2:00 | 2:00
Wednesday | 2020-08-05 | 2020-08-13 |  |  |  |  | 2:00 | 2:00
Thursday | 2020-08-06 | 2020-08-14 |  |  |  |  | 2:00 | 2:00
Friday | 2020-08-07 | 2020-08-17 | SKILL BASED ASSESSMENT - 3 Days (Programming + database based component of main project) - 3 hours Per Day
Monday | 2020-08-10 | 2020-08-18
Wednesday | 2020-08-12 | 2020-08-19
Thursday | 2020-08-13 | 2020-08-20 | 3 Days of Buffer for support session and re-assessment of those who would not be able to clear the SBA with 80% score
Friday | 2020-08-14 | 2020-08-21
Monday | 2020-08-17 | 2020-08-24
Tuesday | 2020-08-18 | 2020-08-25 | Phase 2 | Self Paced | HTML, CSS & JavaScript | HTML CSS and JavaScript for Beginners - A Web Design Course | 15:00 | 3:00
Wednesday | 2020-08-19 | 2020-08-26 | [5 empty] | 3:00
Thursday | 2020-08-20 | 2020-08-27 | [5 empty] | 3:00
Friday | 2020-08-21 | 2020-08-28 | [5 empty] | 3:00
Monday | 2020-08-24 | 2020-08-31 | [5 empty] | 3:00
Tuesday | 2020-08-25 | 2020-09-02 |  | Doubt clearing session VILT for those who couldn’t clear MCQ assessment - 2 Hours
Wednesday | 2020-08-26 | 2020-09-03 |  | VILT | Spring Core SOAP, REST Spring MVC Security, Session Management | Why Spring Setting up development environment XML based configuration Dependency Injection Bean Scopes and Lifecycle Java based configuration What is MVC Why spring MVC What is DispatcherServlet Spring stereotype annotations First Spring controller ViewResolver PathParam, RequestParam, PathVariable, ModelAttribute Validation Introduction to Webservices SOAP vs REST Controller vs RestController Produce and Consume Json & XML response MediaTypes ExceptionHandling SpringTesing Authorization Vs Authentication Restricting URLs Login Form User Detail Service JDBC Uservice Spring Session Spring Session Benefits Spring Session Example SpringBoot introduction First springboot exapmle Bill of materials Spring Initializr configuration file CRUD example thymeleaf for web based applications Live Reload Embedding database H2 database CrudRepository and JpaRepository | 2:00 | 2:00
Thursday | 2020-08-27 | 2020-09-04 |  |  |  |  | 2:00 | 2:00
Friday | 2020-08-28 | 2020-09-07 |  |  |  |  | 2:00 | 2:00
Monday | 2020-08-31 | 2020-09-08 |  |  |  |  | 2:00 | 2:00
Wednesday | 2020-09-02 | 2020-09-09 |  |  |  |  | 2:00 | 2:00
Thursday | 2020-09-03 | 2020-09-10 |  |  |  |  | 2:00 | 2:00
Friday | 2020-09-04 | 2020-09-11 |  |  |  |  | 2:00 | 2:00
Monday | 2020-09-07 | 2020-09-14 |  |  |  |  | 2:00 | 2:00
Tuesday | 2020-09-08 | 2020-09-15 |  |  |  |  | 2:00 | 2:00
Wednesday | 2020-09-09 | 2020-09-16 |  |  |  |  | 2:00 | 2:00
Thursday | 2020-09-10 | 2020-09-18 |  |  |  |  | 2:00 | 2:00
Friday | 2020-09-11 | 2020-09-21 | SKILL BASED ASSESSMENT - 3 Days (UI and front End development of the main application while interfacing with predeveloped backend that’s developed in phase 1) - 3 Hours per day
Monday | 2020-09-14 | 2020-09-22
Tuesday | 2020-09-15 | 2020-09-23
Wednesday | 2020-09-16 | 2020-09-24 | 3 Days of Buffer for support session and re-assessment of those who would not be able to clear the SBA with 80% score
Friday | 2020-09-18 | 2020-09-25
Monday | 2020-09-21 | 2020-09-28
Tuesday | 2020-09-22 | 2020-09-29 | Phase 3 | Self Paced | GIT | Mastering Git and GitHub - A Practical Bootcamp for Beginners | 6:00 | 3:00
Wednesday | 2020-09-23 | 2020-09-30 | [5 empty] | 3:00
Thursday | 2020-09-24 | 2020-10-01 |  | Doubt clearing session VILT for those who couldn’t clear MCQ assessment - 2 Hours
Friday | 2020-09-25 | 2020-10-05 |  | VILT | Maven CI/CD - Jenkins | What is Maven Why Maven Creating our 1st Maven Project Create a Simple Maven Project Create maven web project Maven Plugins Multi-module maven project Maven vs Gradle What is Jenkins What is continuous integration and continuous delivery Getting started with Jenkins Sending emails Ways to trigger a job/build Build with maven Integrate with Git Automated Deployment what is Pipeline How to build a Jenkins pipeline Introduction to docker Build docker container | 2:00 | 2:00
Monday | 2020-09-28 | 2020-10-06 |  |  |  |  | 2:00 | 2:00
Tuesday | 2020-09-29 | 2020-10-07 |  |  |  |  | 2:00 | 2:00
Wednesday | 2020-09-30 | 2020-10-08 |  |  |  |  | 2:00 | 2:00
Thursday | 2020-10-01 | 2020-10-09 |  |  |  |  | 2:00 | 2:00
Monday | 2020-10-05 | 2020-10-12 |  |  |  |  | 2:00 | 2:00
Tuesday | 2020-10-06 | 2020-10-13 | Hackathon preparatory VILT Session 1 Day - 2 Hours Project Explaination & Orientation & 6 Hours revision
Wednesday | 2020-10-07 | 2020-10-14 | HACKATHON (a functional application as an outcome) - 3 Days (integration and deployment with code management ) + code walkthrough 2 days - 3 Hours per Day -
Thursday | 2020-10-08 | 2020-10-15
Friday | 2020-10-09 | 2020-10-16
Monday | 2020-10-12 | 2020-10-19
Tuesday | 2020-10-13 | 2020-10-20
List of Holidays as per National Holiday Calendar
|  |  |  | Friday | 2020-07-31 | Eid
|  |  |  | Monday | 2020-08-03 | Raksha Bandhan
|  |  |  | Tuesday | 2020-08-11 | Janmashtmi
|  |  |  | Tuesday | 2020-09-01 | Onam
|  |  |  | Thursday | 2020-09-17 | Mahalya